## Sheet1
Date | Time/h | Details
2016-02-10 | 6 | dentification of the need and opportunity. Probleme formulation. BRR. Meeting with Radmila the 11th at 11:00.
2016-02-11 | 8 | Meeting with Radmila at 11:00. discussed the different facilities and services we should inspect.
2016-02-12 | 6 | Research different facilities, and different services available
2016-02-15 | 1.5 | Discuss the SE framework, and assigned tasks to each of us
2016-02-17 | 4.5 | 2.5 hours for meeting,2 hours for Paper reading
2016-02-18 | 2 | 2 hours for writing stakeholders and requirement
2016-02-19 | 2 | 2 hours for meeting
2016-02-21 | 3 | rewrite BRR, write SRR 1,2 and CONOPES
2016-02-22 | 1 | Skype meeting with Aurilla.
2016-02-25 | 4 | 3 hours meeting,1hour work for view of conops
2016-02-28 | 1 | 1hours meeting
2016-02-29 | 1 | 1hours group meeting
2016-03-02 | 4 | Change brr accoding to Aurilla's comments
2016-03-06 | 1 | Meeting about BRR, SRR
2016-03-07 | 2.5 | Meeting about SDR
2016-03-09 | 5 | Meeting about solutions and criteria, meeting with Aurilla
2016-03-10 | 5 | meeting about survey questions 9:00-11:00,class meeting 11:00-12:00, redesign questions and survey 14:00-16:00
2016-03-11 | 7 | Conducting Survey, and Interviews. Analysing available answers, discussing the PM document and Conops
2016-03-14 | 4 | analyze survey data, sepreate tasks about conops
2016-03-15 | 4 | conops: changes to current situation
2016-03-16 | 3 | 2 hours meeting,1 hous to finish the survey summary
2016-03-28 | 2 | Conops document.
2016-03-29 | 7 | 3 hours for CONOPS document formate, 4 hours for meeting
2016-03-31 | 5.5 | Conops document. PM document.Stakeholders' requirements.
2016-04-01 | 6 | group meeting
2016-04-04 | 5 | group meeting
2016-04-07 | 5.5 | System requirements, functional analysis
2016-04-08 | 6.5 | meeting with Alrila, group meeting
2016-04-11 | 5 | group meeting
2016-04-13 | 5 | meeting with Alrila, group meeting(9:30 -12:30 2:00-4:00)
2016-04-18 | 1 | skype with Aurilla (Dismissed!) group meeting in classroom.
2016-04-25 | 6 | meeting with Alrila, group meeting(9:30 -12:30 14:00-17:00)
2016-04-26 | 3.5 | continuing working on Aurilla's comments. Seperate tasks about the system possible components.
2016-05-02 | 7.5 | Discussed the serparated tasks done, also the SE documents, and seperated task while working together. Skype meeting dismissed.
2016-05-03 | 5.5 | Review BRR,SRR,PDR,CDR.
2016-05-04 | 3 | Finish PDR
2016-05-05 | 2.5 | Work on the presentation
2016-05-09 | 2 | Presentation summary slides
2016-05-14 | 3.5 | Working on the content of each slide.
2016-05-16 | 7.5 | continute to Working on the content of each slide.
2016-05-18 | 5 | prepare for the presention
170