## Sheet1
Team meetings
Prepared by: Badis Madani
Date | Start-time | Finish-time | Total-time | Tasknr. | Task and description
2016-02-10 | 9:30 | 15:00 | 5:30 | 1.1.1 | Identification of the need and opportunity. Probleme formulation. BRR. Meeting with Radmila the 11th at 11:00.
2016-02-11 | 9:00 | 17:00 | 8:00 | 1.1.2 | Meeting with Radmila at 11:00. discussed the different facilities and services we should inspect.
2016-02-12 | 10:00 | 16:00 | 6:00 | 1.1.3 | Research different facilities, and different services available
2016-02-15 | 11:00 | 12:30 | 1:30 | 1.1.4 | Discuss the SE framework, and assigned tasks to each of us
2016-02-17 | 11:00 | 12:00 | 1:00 | 1.1.5 | Skype meeting with Aurilla.
2016-02-17 | 20:00 | 21:30 | 1:30 | 1.1.6 | discussions: FM in Norway. Aurilla's paper about FM, HVAC service chosen
2016-02-19 | 10:00 | 12:00 | 2:00 | 1.1.7 | Identification of stakeholder and their requirements. BRR. Conops, SRR content. Gantt chart.
2016-02-22 | 11:00 | 12:00 | 1:00 | 1.1.8 | Skype meeting with Aurilla.
2016-02-25 | 10:00 | 13:00 | 3:00 | 1.1.9 | Discussing BRR, SRR and finishing the Conops
2016-02-28 | 15:00 | 16:00 | 1:00 | 1.1.10 | Reviewing the BRR and Conops.
2016-02-29 | 11:00 | 12:00 | 1:00 | 1.1.11 | Skype meeting with Aurilla.
2016-03-01 | 14:00 | 16:30 | 2:30 | 1.1.12 | Discussed the modification of BRR and finished the Gantt chart. We assigned different task for each member.
2016-03-06 | 15:00 | 16:00 | 1:00 | 1.1.13 | Finished BRR and finished SRR. Schedule the next team meetings.
2016-03-07 | 14:00 | 16:30 | 2:30 | 1.1.14 | discussed SDR content. Identification of different design solutions. Contacted a person in Krona, and a company as well.
2016-03-09 | 14:30 | 17:00 | 2:30 | 1.1.15 | Physical meeting with Aurilla; Followed the SE framework. Explained in details the 2 different approaches (Project management, Systems Enginnering).
2016-03-10 | 9:00 | 12:00 | 3:00 | 1.1.16 | Make Survey questions. Meeting all class with Aurilla for project progress. Interview Aurilla about indoor environment.
2016-03-10 | 14:00 | 15:30 | 1:30 | 1.1.17 | Redesign survey questions according to Aurilla’s suggestions.Distribute survey papers to our Interviewees.
2016-03-11 | 9:30 | 16:30 | 7:00 | 1.1.15 | Conducting Survey, and Interviews. Analysing available answers, discussing the PM document and Conops.
2016-03-14 | 9:30 | 13:00 | 3:30 | 1.1.16 | Survey results analysis. Working on Conops document.
2016-03-16 | 9:30 | 11:30 | 2:00 | 1.1.17 | Survey results analysis document. Working on Conops document.
2016-03-28 | 11:00 | 12:00 | 1:00 | 1.1.18 | Conops document.
2016-03-29 | 13:00 | 17:00 | 4:00 | 1.1.19 | Conops document. PM document.
2016-03-31 | 10:00 | 15:30 | 5:30 | 1.1.20 | Conops document. PM document.Stakeholders' requirements.
2016-04-01 | 9:30 | 15:30 | 6:00 | 1.1.21 | Conops document. Stakeholders' requirements. Design concepts, Pugh and AHP matrix.
2016-04-07 | 9:30 | 15:00 | 5:30 | 1.1.22 | System requirements, functional analysis
2016-04-08 | 9:30 | 16:00 | 6:30 | 1.1.23 | skype with Aurilla. System requirements, functional analysis
2016-04-11 | 9:30 | 16:30 | 7:00 | 1.1.24 | SDR and PM documents, system requirements, functional analysis.
2016-04-13 | 9:30 | 15:00 | 5:30 | 1.1.25 | Skype meeting with Aurilla (1h). Conops, system requirements, research on how to regulate humidity and air quality.
2016-04-14 | 13:00 | 16:00 | 3:00 | 1.1.26 | System requirements, functional analysis.
2016-04-18 | 9:30 | 10:30 | 1:00 | 1.1.27 | skype with Aurilla (Dismissed!) group meeting in classroom.
2016-04-25 | 9:30 | 15:30 | 6:00 | 1.1.28 | Meeting with Aurilla (1h). Group meeting in the Lab. Seperate tasks according to Aurilla's comments.
2016-04-26 | 13:00 | 16:30 | 3:30 | 1.1.29 | continuing working on Aurilla's comments. Seperate tasks about the system possible components.
2016-04-28 | 9:30 | 11:30 | 2:00 | 1.1.30 | hardware components, Hw block diagram. Discuss the next tasks and how it is intended to proceed. Discuss the agenda.
2016-05-02 | 9:30 | 17:00 | 7:30 | 1.1.31 | Discussed the serparated tasks done, also the SE documents, and seperated task while working together. Skype meeting dismissed.
2016-05-03 | 12:30 | 18:00 | 5:30 | 1.1.32 | Review BRR,SRR,PDR,CDR.
2016-05-05 | 13:30 | 16:00 | 2:30 | 1.1.33 | Review BRR,SRR,PDR,CDR.
2016-05-09 | 9:30 | 11:30 | 2:00 | 1.1.34 | Sent Aurilla an email. Worked on the presentation content.
2016-05-14 | 9:30 | 13:00 | 0.14583 | 1.1.35 | Worked on the presentation content.
2016-05-16 | 9:30 | 17:00 | 0.3125 | 1.1.36 | Worked on the presentation content.
2016-05-18 | 9:30 | 14:30 | 0.20833 | 1.1.37 | Rehearse the presentation.
1900-01-05 03:00
Formulas:
Total-time = SUM(D7:[Total-time, row above])